## Slide 1
Training package on active tuberculosis drug safety monitoring and management (aDSM)
2023

## Slide 2
2.1ii. Develop a plan for aDSM

## Slide 3
Key steps in aDSM implementation
Create a national coordinating mechanism for aDSM
Develop a plan for aDSM
Define management and supervision roles and responsibilities
Create standard data collection materials
Train staff on the collection of data
Define schedules and routes for data collection and reporting
Consolidate aDSM data electronically
Develop capacity for signal detection and causality assessment

## Slide 4
Explain the main activities and timelines needed in an implementation plan for aDSM at country level
Learning objective By the end of this presentation, the participant is expected to be able to:

## Slide 5: Timeline for aDSM implementation (1)
An example GANTT chart showing timelines for all activities needed in preparation for aDSM for the programmatic introduction of new drugs or regimens is shown on the following slide
Each activity listed in the chart will need to be costed and matching resources identified
Sub-activities also need to be developed; more detail available in other slide sets in this module

## Slide 6
Activities | Months before start |  |  |  |  |  | START
 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Establish national coordinating mechanism for aDSM |  |  |  |  |  |  | 
Develop aDSM implementation plan |  |  |  |  |  |  | 
Decide on paper or electronic system to be used for aDSM data collection |  |  |  |  |  |  | 
Training on aDSM (for national PV centre, for clinicians/nurses, for data-entry staff, etc.) |  |  |  |  |  |  | 
Define roles and responsibilities at each NTP level, and between NTP and national PV centre |  |  |  |  |  |  | 
Develop work plan and budget |  |  |  |  |  |  | 
Define the local list of data elements and data dictionary |  |  |  |  |  |  | 
Include aDSM data elements in MDR-TB care data collection tools |  |  |  |  |  |  | 
Adjust data monitoring and evaluation system |  |  |  |  |  |  | 
Develop data management plan |  |  |  |  |  |  | 
Develop standard operating procedure (SOP) |  |  |  |  |  |  | 
Pilot data collection and processing up to national level |  |  |  |  |  |  | 
Implement aDSM |  |  |  |  |  |  | 
Timeline for aDSM implementation (2)

## Slide 7: Establish a national coordinating mechanism for aDSM
Time for completion
  Two months
  Start six months prior to aDSM implementation
Sub-tasks
  Include representatives from the NTP, the national PV center, and MDR-TB clinical experts from facilities
  Develop terms of reference for the committee
  Refer to Module 2.1i (Create a national coordinating mechanism for aDSM)

## Slide 8: Develop aDSM implementation plan
Time for completion
  Three months
  Start six months prior to aDSM implementation
Sub-tasks
  Make and document decisions about
    what needs to be done
    who does what, when, and where
  Steps described in the following slides will help plan for a successful strategy

## Slide 9: Decide on paper or electronic system for aDSM data collection
This activity is a relative priority given that the collection of data is key
Time for completion
  Two months
  Start six months prior to aDSM implementation
Sub-tasks
  NTPs that manage programme data using electronic systems with data quality assurance processes in place may be able to obtain aDSM data collected regularly electronically
  Ensure aDSM can be integrated into routine system used for MDR-TB surveillance

## Slide 10: Conduct aDSM Training
This activity is a relative priority to ensure that the collection of data (in prior slide) proceeds well
Time for completion
  One month
  Start two months prior to aDSM implementation
Sub-tasks
  Define staff to be trained
  Plan post-implementation new staff training
  Plan post-implementation refresher trainings
  Refer to other relevant modules in this series, especially
    module 2.1v for data collection training and
    module 2.1viii for capacity building

## Slide 11: Develop Work Plan and Budget
Time for completion
  Two months
  Start five months prior to aDSM implementation
Sub-tasks
  Analyze each for resource requirements.
  Estimate cost of supplies, travel, and time needed by employees
  Conduct a feasibility check to see if staff will actually have time available to do the work
  Refer to Module 3.5 for partner contributions

## Slide 12: Define roles and responsibilities
Time for completion
  Two months
  Start five months prior to aDSM implementation
Sub-tasks
  Refer to module 2.1iii (Management, supervision and roles and responsibilities) and
  and 2.1viii (Capacity building)

## Slide 13: Define the local list of data elements and data dictionary
Time for completion
  Two months
  Start five months prior to aDSM implementation
Sub-tasks
  Decide on a coding dictionary, and grading scales to be used nationally
    National Cancer Institute Common Terminology Criteria for Adverse Events (NCI-CTCAE)
    Division of Microbiology and Infectious Diseases (DMID) Adult Toxicity Table

## Slide 14: Include aDSM data elements in MDR-TB care data collection tools
Time for completion
  One month
  Start three months prior to aDSM implementation
Sub-tasks
  Update AE and SAE forms
  Update standard treatment forms
  Refer to Modules
    2.1iv (Create standard data collection materials) and
    2.1.vii (Consolidate aDSM data electronically)

## Slide 15: Adjust monitoring and evaluation system to incorporate aDSM
Time for completion
  One month
  Start three months prior to aDSM implementation
Sub-tasks
  Conduct a feasibility check
  Pilot adjustments
  Revise adjustments if appropriate
  Refer to modules
    2.1iv and 2.1vii in this series

## Slide 16: Develop data management plan
Time for completion
  Two months
  Start four months prior to aDSM implementation
Sub-tasks
  Ensure processes and procedures are in place for:
    collecting
    monitoring
    handling
    storing
    storing
    processing
    Validating and archiving of data

## Slide 17: Develop SOP
Time for completion
  Two months
  Start three months prior to aDSM implementation
Sub-tasks
  Adjust existing SOP
  Ensure every SOP includes:
    Introduction of the procedure
    For which staff members it is applicable
    Step-by-step description of the procedure
    Frequency and/or specific timing
    Expected results/outcomes

## Slide 18: Pilot data collection and processing up to national level
Time for completion
  One month
  Start one month prior to aDSM implementation
Sub-tasks
  Adjust technical system (if needed)
  Adjust and retest at national level
  Adjust SOPs (if needed)

## Slide 19: Conclusions
The aDSM plan needs to try and describe the different components which need to come together in order for aDSM to be successfully completed over a reasonable period of time (e.g. 6 months)
The plan needs to identify appropriate domestic and external funding which can be brought together in order to make aDSM a reality
The critical steps will be to establish : a national coordinating mechanism; roles and responsibilities of different national actors; recording and reporting parameters; data management (electronic); and to train staff on aDSM

## Slide 20
Acknowledgements
The development of the aDSM training material was funded by TDR as part of the Access and Delivery Partnership (ADP) with funding from the Government of Japan.
These training materials were put together in 2016 the WHO Task Force on aDSM with technical partners KNCV Tuberculosis Foundation, Management Sciences for Health (SIAPS), MSF, WHO GTB, and TDR.
The materials were updated in 2022-23 by Mahamadou Bassirou Souleymane (TDR consultant) with Marie-Eve Raguenaud (TDR), Branwen J Hennig (TDR), and Corinne Merle (TDR), and reviewed by Linh Nhat Nguyen (WHO/GTB), Medea Gegia (WHO/GTB), and Fuad Mirzayev (WHO/GTB).
We thank all members of the WARN/CARN-TB working group on aDSM who contributed to the development of the aDSM generic guidelines as well as the secretariat, particularly Dr Christ Houessinon: Disadidi Ambrioso, Esse Marius, Adomou Jamal Rouamba Ruffine, Haro Sougrimani, Koumbem Boureima, Nsanzerugeze Josélyne, Tollo Tollo Daniel Alphonse Désiré, Mpaba Minkat Théophile Mistral, Julie Abessolo, Ursule IDOKO, Tijan Baldeh , Wandifa Samateh, Tida S Kinteh, Alieu Wurie, Mardemn Yeasuen, Benjamin K. Quenneh, Cheick Oumar Bah, Kane El Hadj Malick, Aw Idriss, Mamoudou Hama Rachida, Gagara I. M. Assiatou, Katambé Balkissa, Seiyabatou Elh Saidou, Liombo Anastasie, Lunganyu Junior, Kitambala Sentime, Lula Yves , Habimana-Mucyo Yves, Migambi Patrick, dos Santos Brigite, Castro Vânia, Wadson Cruz, Gueye Aminata, Mukeh Fahnbulleh, Bailor Samuel, Manjo Lamin, Saleh Mahareb Abdoulaye, Haroun Saleh Naima, Mouhoudine Yerima, Kpelafia Silifa